## Function Point Method
Function Point Method
Type | Factor | Number | Function Points
Inputs (EI) | 4 | 1 | 4
Outputs (EO) | 5 | 7 | 35
Queries (EQ) | 4 | 0 | 0
Internal files (ILF) | 10 | 0 | 0
External files (EIF) | 7 | 2 | 14
Total Function Points |  |  | 53
Method: Unadjusted Function Points. Each component count is multiplied by its factor. The resulting total of 53 FP is used as the size basis for the LOC estimate.

## LOC & COCOMO
LOC & COCOMO – Organic Mode
Size Estimation
Metric | Value
Function Points | 53
LOC per Function Point | 16
Estimated LOC | 848
Estimated KLOC | 0.848
COCOMO Organic Mode Calculation
Metric | Formula / Assumption | Result | Unit
Effort | 2.4 × (KLOC)^1.05 | 2.0185 | person-months
Development Time | 2.5 × (Effort)^0.38 | 3.2648 | months
Implied Team Size | Effort ÷ Time | 0.61827 | FTE
Effort Hours | Effort × hours per person-month | 322.9586 | hours
Hours per Person-Month | Planning assumption | 160 | hours
Interpretation: Based on 53 Function Points and 16 LOC per Function Point, the estimated size is 848 LOC (0.848 KLOC). Basic COCOMO in Organic Mode estimates approximately 2.02 person-months of effort, 3.26 months of calendar time and an implied average team size of 0.62 FTE.

## Cost Comparison
Cost Comparison – Working Students vs. Regular Developer
Shared Workload Assumption
Assumption | Value
Total estimated effort | 322.9586
Working weeks per month | 4.33
Scenario | Employees | Hours / Employee / Week | Team Hours / Week | Project Duration (Weeks) | Project Duration (Months) | Rate | Cost
Working Students | 3 | 20 | 60 | 5.3826 | 1.2431 | 23 | 7428.0481
Regular Developer | 1 | 40 | 40 | 8.074 | 1.8647 | 50 | 16147.9306
Category | Recommended Percentage | Estimated Cost (Student Team) | Estimated Cost (Regular Developer) | Notes
Developer Cost |  | 7428 | 16147.9
Project Management & Coordination | 15% | 1114.2 | 2422.185 | These are rough estimates
Change Management & Training | 5% | 371.4 | 807.395 | These are rough estimates
Contingency Buffer | 10% | 742.8 | 1614.79 | These are rough estimates
SUM |  | 9656.4 | 20992.27